Action	Time
Local Development Scheme considered by Cabinet	July 2018
Growth and Infrastructure Strategy preparation begins	July / August 2018
Local Plan update report to Cabinet to consider Issues & Options consultation responses, implications of new NPPF, confirmation of new housing requirements arising from the Government's standard methodology and progress of key Local Plan work	October 2018
Growth and Infrastructure Strategy considered by Cabinet and Council	December 2018
Local Plan update report to Cabinet on key evidence reports	February 2019
Site evaluation and selection report considered by Cabinet	May 2019
Draft Pre-Submission Local Plan considered by Cabinet and Council	July – September 2019